## Checklist Instructions
MMIS Certification Checklist - MECT2.2
Checklist: |  |  | Member Management Checklist (MITA Module)
Sources for this Checklist: Note: References to specific regulations or policy are provided for new draft criteria and are for informational purposes only during development of the pilot prototype. The criteria contained in the prototype are not final and additional regulations or policy not listed may also apply.
Note: Some of these instructions are MMIS specific.
Checklist Instructions
A. | General Information – What users need to know about the Checklists
B. | State and IV&V Specific Instructions – The process of completing the Checklist by the state
C. | Sample Criteria and Evidence – Sample evidence in each of the Milestone Review phases
General Information:
· | (MMIS specific) Depending on approved MMIS development option, state selects the appropriate checklist set.
¾ MITA Checklist Set: Ten (10) MITA + Core Checklists (IA Component, TA Access And Delivery, TA Intermediary and Interface, TA Integration and Utility, and Standards and Conditions)
¾ MMIS Functional Checklist Set: Ten (10) MMIS Checklists + Core Checklists
¾ Custom Set: One workbook to develop custom set of modular checklist(s) + Core checklists. The Custom Set option must be developed in coordination with and receive approval by CMS.
· The checklists are used for documenting state evidence and IV&V reviewer comments. When completed, checklist data will be imported into a CMS tracking database.
· The first 27 columns are grouped into three sections identified by headers to identify data. The headers are read-only and should not be edited. These are identified as follows:
¾ Columns (col) A to C are criteria information labeled as: Ref #, System Review Criteria, and Source respectively.
Criteria Ref # pattern: MITA Business Area.CSF Code.Unique Number (e.g. CA.CL7.1)
MITA State Specific Criteria Ref# : MITA Business Architecture.Business Area.Business Process.State Abbr.Unique Number (e.g. BA.CM.FFS.SS.NY.1)
MITA Architecture (TA, IA, S&C) : MITA Architecture.MITA component.Unique Number (e.g. S&C.BRC.1, TA.SP.33, IA.CDM.1)
¾ Entrees in col A are color-coded to indicate status of the criteria (red italics: state-specific)
¾ Col pairs D and E, J and K, and P and Q are for entering state Evidence data. Each pair is labeled Yes/No/Not Applicable and X Evidence Comments where X is the Milestone Review
¾ Col sets F to I, L to O, and R to U are for entry of IV&V reviewer comments for each of the Milestone Review phases.
¾ Each set includes Review Date, Reviewer Name, Reviewer Assessment, and Reviewer Comments
· The column structure (i.e. label names, merged columns, etc.) is used by the database during import of the checklist data and should not be changed
· Criteria in each checklist are grouped into a series of rows. Each group begins with a merged row colored in green to mark the beginning of a group mapping
¾ Depending on the package used, each green merged row identifies either a business process, technical service, component, or module
State and IV&V Specific Instructions:
· Complete criteria evidence columns prior to each milestone review
· IV&V will work with state to review evidence and annotate review findings and resolutions in the review columns of the checklist
· "Not assessed" is chosen if the IV&V contractor does not assess a criterion. The contractor should indicate in the comments column why it was not assessed.
· "Not Applicable" is chosen if the state does not deem a criterion to apply to its module(s). The state must indicate in the evidence column why it does not apply.
The IV&V contractor must evaluate whether it does or does not apply and indicate whether it concurs or disagrees with the state in the review comments column.
· "Partially meets" is chosen if the module(s) meets some but not all aspects of the criterion.
· "Doesn't meet" is chosen if the module(s) completely fails to meet the criterion.
· Evidence columns (D-E for Project Initiation, J-K for Operational, and P-Q for Final) and Review columns (F-I for Project Initiation, L-O for Operational, and R-U for Final):
¾ The evidence pair columns have “Yes/No/Not Applicable” to indicate criteria has been met or out-of-scope and "Comments" for entry of supporting evidence text
¾ Criteria evidence will be entered in the same row as the criteria under each Milestone Review phase
¾ Criteria evidence references to artifacts should be as specific as possible, including section or page numbers, so that the cited evidence can be readily confirmed
¾ Do not change Criteria Numbers (Ref #s). Ref #s are unique. Renumbered criteria will be rejected during the import process
¾ Yes in the Yes/No column requires entry of compliance evidence indicating that the criteria has been complied with. Enter No if not applicable or out of scope then add evidence why.
¾ Evidence text in the Evidence column can be hyperlinked to a supporting document (only one link is currently allowed per cell)
· Source column showing MITA level # (e.g. col. C = MITA Level 2) requires entry of compliance evidence when To-Be Maturity target is equal or below the indicated number
· Important!!! Do not rename checklist. Instead, append to existing filename the state full name for identification purposes (e.g. Care Management Checklist (MITA Module) Ohio.xlsm)
The filename helps identify the state owner of the checklist and the development approach used which is required to successfully upload the data in the database.
· Do not rename the tabs (worksheets) within the checklist. The sheet name is used by the tracking database to associate data to target tables in the database
· Any state specific criteria will be submitted to and discussed with CMS prior to incorporating into the checklists
Guidance Tab (Applies to Core Checklists):
· A guidance tab is included in the Core Checklists. This is intended to help states and their IV&V contractors to understand the type of evidence that would be appropriate for each criterion.
· Guidance often includes statements such as "evidence could include…" If the state can prove compliance to the criteria with artifacts and demonstrations other than those suggested, that is fine.
· Sometimes clarification is given for how a state can meet a criterion from a perspective that spans multiple modules. These statements start with "Enteprise:"
· Sometimes clarification is provided for how a single module moving through a milestone could show compliance to a criterion. These statements start with "Module:"
· Most criterion apply across the enterprise and for individual modules.
· Criteria that do not apply to Eligibility and Enrollment modules are noted as such.
Sample Criteria and Evidence Data (Applies to Non-Core Checklist):
Ref # | System Review Criteria |  |  | Project Initiation Milestone Potential Artifacts: RFP, CONOPS, SLA, BPM, MITA | Operational Milestone Review Potential Requirements and/or Design Artifacts: Requirements Specification Document (RSD), Use Cases, Security Plan, LDM), Design Document, ICD, PDM, RTM, Test Cases | Final Milestone Certification Review (MMIS) Potential Artifacts: Test Results, Operational Data
CA.CL7.1 | Processes and retains all prior authorization request data. |  |  | RFP entry: System will process and retain data for all prior authorization requests (RFP document name/pg. # with accessible link to document location). | RSD entry: The system shall process and retain data for all prior authorization request (RSD document name/pg. # with accessible link to document location). Design document entry: system behavior (function) that processes and persists all authorization request data (Design document name/pg. # with accessible link to document location). | Test Result: Report output showing history of processed authorization requests within a given time frame (accessible link to a sample report location).
PE.PH6.2 | Prepares extracts of pharmacy claims history (or access to the claims history) for purposes of retrospective DUR, prescriber and pharmacy provider profiling, management reporting, and other decision support functions. |  |  | RFP: Maintain pharmacy claims history (or access to claims history) for purposes of retrospective drug utilization review (DUR), prescriber and pharmacy provider profiling, management reporting and other decision support functions. | RSD: The system shall maintain pharmacy claims history for the purposes of retrospective drug utilization review (DUR), prescriber and pharmacy provider profiling, management reporting and other decision support functions. Design document: Pharmacy claims database specifications. Design supports RetroDUR and related prescriber and pharmacy provider management and decision-making. Includes specifications for data persistence/archiving and reporting functions. | Test result: Documentation of pharmacy claims for RetroDUR and related prescriber and pharmacy provider management and decision-making. Support for statistical analysis and short and long term reporting.